## 1. Task Sheet
PROJECT PLAN - HALO ARMS TICKETING
Tasks | Assigned To | Start Date | End Date | Health | Status | Brief Description
INITIATION
Conceptualise the Idea (proof of concept) | Camille Ydel | 2021-07-17 | 2022-08-29 | Green | Complete | Halo Arms Ticketing innovative idea created
Obtain business loan (soon as grant approved) | Camille Ydel | 2022-08-13 | 2022-08-15 | Red | Not Started | Sought funding through business loan
Proposal for Grant Funding | Camille Ydel | 2022-08-29 | 2022-11-07 | Yellow | In Progress | Application for Arts & Cultural Grant Funding
Community Engagement | Camille Ydel | 2022-07-17 | 2022-08-27 | Green | Complete | Council & Local MPs
Research | Camille Ydel | 2022-07-17 | 2022-08-07 | Green | Complete | Statistical study
Feasible Study | Camille Ydel | 2022-01-02 | 2022-08-02 | Green | Complete | Statistics and research Analysis
SYSTEMS
Develop Interface System eCommerce | Software Company | 2022-10-03 | 2023-01-09 | Red | Not Started | Sought Software Company to create system infrastructure
Create Web Design through IP address (www.haloarmstickets.com.au) | Software Company | 2022-07-04 | 2022-12-12 | Yellow | In Progress | Sought Software Company to create system infrastructure
Application software to be created to sell tickets online | Software Company | 2022-12-19 | 2023-02-27 | Red | Not Started | Sought Software Company to create system infrastructure
STAKEHOLDER ENGAGEMENT
(First Phase)
Partnering with NSW Theatres in the minor/major groups | Local Theatres | 2022-12-05 | 2023-03-31 | Red | Not Started | Enter into network partnerships with NSW Theatre companies
Set up meeting to present idea | Camille Ydel | 2022-12-12 | 2023-02-28 | Red | Not Started | Relationship building with local networks
Contract Creation and Signing Agreements | Local Theatres | 2023-03-06 | 2023-03-31 | Red | Not Started | Legal Agreements entered into with network partners
(Second Phase)
Plan for busines expansion with local business such Travel & Tourist and Dining experiences. | Local Partnerships | 2023-12-04 | 2023-06-30 | Red | Not Started | Local business partners entering in business networks
Value packages put together 'Dinner & Show'. | Local Partnerships | 2023-12-04 | 2024-07-15 | Red | Not Started | Local business partners entering in business networks
(Third Phase)
Expansion through Hotel Accommodation Packages e.g. "Dinner. Show & Accommodation" | Local Partnerships | 2023-12-04 | 2024-12-16 | Red | Not Started | Local business partners entering in business networks
STAFF RECRUITMENT
Recruit Staff Personnel: |  | 2023-01-16 | 2023-02-16 | Red | Not Started
First Recruiment: Manager, 2 x Casual Staff | Staff | 2023-07-03 | 2023-07-24 | Red | Not Started | Recruitment of Staff
Second Recruitment: Business Relationship Manager & Finance Manager | Staff | 2024-07-01 | 2024-07-31 | Red | Not Started | Recruitment of Staff
Third Recruitment: Business Development Manager | Staff | 2025-07-07 | 2025-07-31 | Red | Not Started | Recruitment of Staff
LOCATIONS (LEASE)
First proposed location: 1st option: Pitt St Mall or Town Hall | Realestate Leasing | 2022-12-05 | 2022-12-30 | Red | Not Started | Lease building or retail space in the CBD area
2nd option: Circular Quay or Martin Place | Realestate Leasing | 2023-07-03 | 2023-07-28 | Red | Not Started | Lease building or retail space in the CBD area
Start business operation in first year | Realestate Leasing | 2022-12-05 | 2022-12-30 | Red | Not Started | Lease building or retail space in the CBD area (1st year)
Second Opening in the following year (2nd) | Realestate Leasing | 2023-07-03 | 2023-07-28 | Red | Not Started | Lease building or retail space in the CBD area (2nd year)
MARKETING
Seek opportunities in NSW to promote business | Camille / Staff | 2022-11-28 | 2023-06-30 | Red | Not Started | Marketing and advertising in the local area.
Local Arts Magazine 'Create' | Camille / Staff | 2022-11-28 | 2023-06-30 | Red | Not Started | Marketing and advertising in the local area.
Online Advertising | Camille / Staff | 2022-11-28 | 2023-06-30 | Red | Not Started | Marketing and advertising in the local area.
Billboards in CBD | Camille / Staff | 2023-06-30 | 2023-12-15 | Red | In Progress | Marketing and advertising in the local area.
Local Partnership such Travel Agencies, Tourist Offices | Camille / Staff | 2023-06-30 | 2023-12-15 | Red | Not Started | Expand in business opportunities.